## Sheet1
Functional Location | Description of functional location | Maintenance strategy | Maintenance Plan | Maintenance item | Maintenance item description | MaintPlan dscrptn | Order | Calendar Week | Planned Date | Work center | Number | Normal duration | MntPlan Call No. | Due Packages | Notification | Notification type | Call Status | Maintenance plant | Material Description | Planner group | Task list description
6042.10.02.61-GR001 | Grader Caterpillar 16M G5008 | PHRN01 | 30797548 | 21249849 | 10000H Ovhl Grader Midlife G5008 | Ovhl Grader Midlife G5008 | 428593339 | 2018/17 | 2018-04-24 | SN43-G03 | 1 | 7 | 1 |  |  |  | RestartCompleted (Work Order) | M201 |  | M04 | 10000H Ovhl Grader Midlife 16M
6042.10.02.61-GR001 | Grader Caterpillar 16M G5008 | PHRN01 | 30318190 | 20452709 | 250H Mech Svce & Lube Grader G5008 | Mech Svce & Lube Grader G5008 | 422540502 | 2013/42 | 2013-10-15 | MN30-F01 | 1 | 1 | 1 |  |  |  | Cycle StartCompleted (Work Order) | M201 |  | M03 | 250H Mech Svce & Lube Schedule 16M
6042.10.02.61-GR001 | Grader Caterpillar 16M G5008 | TWKN01 | 30319873 | 20862026 | 6M Stat Audit Fire System QTEC G5008 | Stat Audit Fire Systems G5008 | 428894189 | 2018/24 | 2018-06-12 | MN30-F01 | 1 | 10.5 | 10 |  |  |  | ScheduledCompleted (Work Order) | M201 |  | M03 | 6M Stat Audit Fire System HYBRID 16M
6042.10.02.61-GR001 | Grader Caterpillar 16M G5008 | PHRN01 | 30316704 | 20450335 | 6000H Mech Calb Pilot Hydraulic G5008 | Calb Pilot Hydraulic G5008 | 423307636 | 2014/13 | 2014-03-26 | MN30-F03 | 1 | 6 | 1 |  |  |  | RestartCompleted (Work Order) | M201 |  | M03
6042.10.02.61-GR001-DRIV | Drive G5008 | PHRN01 | 30318092 | 20452506 | 20000H Repl Axle Assembly Rear G5008 | Repl Axle Assembly Rear G5008 | 426211097 | 2015/47 | 2015-11-17 | MN30-F03 | 2 | 12 | 3 |  |  |  | RestartCompleted (Work Order) | M201 |  | M04
6042.10.02.61-GR001-DRIV | Drive G5008 | PHRN01 | 30318199 | 20452718 | 14000H Repl Wheel & Brake Grup LHR G5008 | Repl Wheel & Brake Grp LHR G5008 | 426211098 | 2015/46 | 2015-11-09 | MN30-F03 | 1 | 15 | 3 |  |  |  | RestartCompleted (Work Order) | M201 |  | M04
6042.10.02.61-GR001-DRIV | Drive G5008 | PHRN01 | 30319558 | 20454584 | 10000H Repl Powertrain Hoses G5008 | Repl Powertrain Hoses G5008 | 422541381 | 2013/45 | 2013-11-09 | MN30-F03 | 2 | 20 | 1 |  |  |  | RestartCompleted (Work Order) | M201 |  | M04
6042.10.02.61-GR001-DRIV | Drive G5008 | PHRN01 | 30319205 | 20454109 | 20000H Repl Transmission G5008 | Repl Transmission G5008 | 426211104 | 2015/46 | 2015-11-09 | MN30-F03 | 1 | 6 | 3 |  |  |  | RestartCompleted (Work Order) | M201 |  | M04
6042.10.02.61-GR001-EICO | Elec Instrument & Ctrl Comp G5008 | PHRN01 | 30317451 | 20451454 | 20000H Repl Alternator G5008 | Repl Alternator G5008 | 423523020 | 2014/18 | 2014-05-02 | MN30-F03 | 1 | 10 | 1 |  |  |  | RestartCompleted (Work Order) | M201 |  | M04 | 8000H Repl Alternator
6042.10.02.61-GR001-EICO | Elec Instrument & Ctrl Comp G5008 | PHRN01 | 30319835 | 20454919 | 20000H Repl Starter Motor G5008 | Repl Starter Motor G5008 | 423523040 | 2014/18 | 2014-05-02 | MN30-F03 | 1 | 10 | 1 |  |  |  | RestartCompleted (Work Order) | M201 |  | M04 | 8000H Repl Starter Motor
6042.10.02.61-GR001-ENGI | Engine G5008 | PHRN01 | 30318200 | 20452719 | 20000H Ovhl Radiator G5008 | Ovhl Radiator G5008 | 426211099 | 2015/46 | 2015-11-09 | MN30-F03 | 2 | 6 | 3 |  |  |  | RestartCompleted (Work Order) | M201 |  | M04
6042.10.02.61-GR001-ENGI | Engine G5008 | PHRN01 | 30854858 | 21359882 | 20000H Repl Fuel Injectors G5008 | Repl Fuel Injectors G5008 | 429539947 | 2019/01 | 2019-01-06 | MN30-F03 | 1 | 4 | 1 |  |  |  | RestartCompleted (Work Order) | M201 |  | M04
6042.10.02.61-GR001-ENGI | Engine G5008 | PHRN01 | 30317511 | 20451540 | 20000H Repl Turbocharger G5008 | Repl Turbocharger G5008 | 428827057 | 2018/20 | 2018-05-19 | MN30-F03 | 1 | 2 | 4 |  |  |  | RestartCompleted (Work Order) | M201 |  | M04
6042.10.02.61-GR001-ENGI | Engine G5008 | PHRN01 | 30316805 | 20450492 | 20000H Repl Engine G5008 | Repl Engine G5008 | 426194502 | 2015/39 | 2015-09-27 | MN30-F03 | 1 | 20.5 | 2 |  |  |  | ScheduledCompleted (Work Order) | M201 |  | M04
6042.10.02.61-GR001-HYSY | Hydraulic System G5008 | PHRN01 | 30317920 | 20452206 | 20000H Repl Motor Fan Drive G5008 | Repl Motor Fan Drive G5008 | 423523021 | 2014/18 | 2014-05-02 | MN30-F03 | 1 | 10 | 1 |  |  |  | RestartCompleted (Work Order) | M201 |  | M04
6042.10.02.61-GR001-HYSY | Hydraulic System G5008 | PHRN01 | 30320772 | 20456200 | 20000H Repl Pump Hydraulic Fan G5008 | Repl Pump Hydraulic Fan G5008 | 428827095 | 2018/20 | 2018-05-19 | SN43-G03 | 1 | 0.5 | 4 |  |  |  | RestartCompleted (Work Order) | M201 |  | M04 | 20000H Repl Hydraulic Fan Pump 16M
6042.10.02.61-GR001-HYSY | Hydraulic System G5008 | PHRN01 | 30317361 | 20451318 | 20000H Repl Pump Secondary Steer G5008 | Repl Pump Secondary Steering G5008 | 426194580 | 2015/37 | 2015-09-10 | MN30-F03 | 1 | 3 | 3 |  |  |  | ScheduledCompleted (Work Order) | M201 |  | M04
6042.10.02.61-GR002 | Grader Caterpillar 16M G5009 | PHRN01 | 30797549 | 21249850 | 10000H Ovhl Grader Midlife G5009 | Ovhl Grader Midlife G5009 | 427777706 | 2017/13 | 2017-04-01 | MN30-F03 | 2 | 10.5 | 1 |  |  |  | RestartCompleted (Work Order) | M201 |  | M04 | 10000H Ovhl Grader Midlife 16M
6042.10.02.61-GR002 | Grader Caterpillar 16M G5009 | PHRN01 | 30732069 | 21140077 | 6000H Mech Calb Pilot Hydraulic G5009 | Calb Pilot Hydraulic G5009 | 425931113 | 2015/32 | 2015-08-03 | MN30-F03 | 1 | 6 | 90000000 |  |  |  | ManualCompleted (Work Order) | M201 |  | M03
6042.10.02.61-GR002 | Grader Caterpillar 16M G5009 | PHRN01 | 30732060 | 21140066 | 4000H Calb Electronics G5009 | Calb Electronics G5009 | 4200414689 | 2019/39 | 2019-09-23 | MN30-E01 | 1 | 6 | 6 |  |  |  | ScheduledCompleted (Work Order) | M201 |  | M03
6042.10.02.61-GR002 | Grader Caterpillar 16M G5009 | PHRN01 | 30317856 | 20452122 | 250H Mech Svce & Lube Grader G5009 | Mech Svce & Lube Grader G5009 | 422707936 | 2013/49 | 2013-12-02 | MN30-F01 | 1 | 15 | 3 |  |  |  | ScheduledCompleted (Work Order) | M201 |  | M03 | 250H Mech Svce & Lube Schedule 16M
6042.10.02.61-GR002 | Grader Caterpillar 16M G5009 | PHRN01 | 30317856 | 21391701 | 500H Mech Svce & Lube Grader G5009 | Mech Svce & Lube Grader G5009 | 4201868485 | 2021/43 | 2021-10-31 | MN30-E01 | 1 | 1 | 161 |  |  |  | ScheduledCompleted (Work Order) | M201 |  | M03 | 500H Mech Svce & Lube Schedule 16M
6042.10.02.61-GR002 | Grader Caterpillar 16M G5009 | TWKN01 | 30319015 | 20453846 | 6M Stat Audit Fire System QTEC G5009 | Stat Audit Fire Systems G5009 | 428070655 | 2017/33 | 2017-08-16 | MN30-F01 | 1 | 10.5 | 8 |  |  |  | ScheduledCompleted (Work Order) | M201 |  | M03 | 6M Stat Audit Fire System HYBRID 16M
6042.10.02.61-GR002 | Grader Caterpillar 16M G5009 | TWKN01 | 30319015 | 21387904 | 60M Stat Audit Fire System QTEC G5009 | Stat Audit Fire Systems G5009 | 4201042664 | 2020/22 | 2020-05-29 | MN30-F01 | 1 | 10.5 | 14 |  |  |  | Cycle StartCompleted (Work Order) | M201 |  | M03 | 60M Stat Audit Fire System LOP 16M
6042.10.02.61-GR002-DRIV | Drive G5009 | PHRN01 | 30796223 | 21248016 | 14000H Repl Wheel & Brake Grup RHR G5009 | Repl Wheel & Brake Grp RHR G5009 | 428732123 | 2018/24 | 2018-06-14 | SN43-G03 | 1 | 0.5 | 1 |  |  |  | RestartCompleted (Work Order) | M201 |  | M04 | 14000H Repl Wheel & Brake Grup Rear 16M
6042.10.02.61-GR002-DRIV | Drive G5009 | PHRN01 | 30796222 | 21248015 | 14000H Repl Wheel & Brake Grup RHF G5009 | Repl Wheel & Brake Grp RHF G5009 | 428732122 | 2018/24 | 2018-06-14 | SN43-G03 | 1 | 1 | 1 |  |  |  | RestartCompleted (Work Order) | M201 |  | M04
6042.10.02.61-GR002-DRIV | Drive G5009 | PHRN01 | 30732035 | 21140009 | 10000H Repl Powertrain Hoses G5009 | Repl Transmission & Hoses G5009 | 425909164 | 2016/32 | 2016-08-12 | MN30-F03 | 2 | 20 | 1 |  |  |  | RestartCompleted (Work Order) | M201 |  | M04
6042.10.02.61-GR002-DRIV | Drive G5009 | PHRN01 | 30732035 | 21140010 | 20000H Repl Transmission G5009 | Repl Transmission & Hoses G5009 | 428962114 | 2018/36 | 2018-09-03 | SN43-G03 | 1 | 0.5 | 4 |  |  |  | ScheduledCompleted (Work Order) | M201 |  | M04 | 20000H Repl Transmission 16M
6042.10.02.61-GR002-DRIV | Drive G5009 | PHRN01 | 30732047 | 21140012 | 20000H Repl Axle Assembly Rear G5009 | Repl Axle Assembly Rear G5009 | 428732111 | 2018/24 | 2018-06-14 | SN43-G03 | 1 | 0.5 | 1 |  |  |  | RestartCompleted (Work Order) | M201 |  | M04 | 20000H Repl Axle Assembly Rear 16M
6042.10.02.61-GR002-DRIV | Drive G5009 | PHRN01 | 30732048 | 21140013 | 20000H Repl Driveshaft Uvsl G5009 | Repl Driveshaft Uvsl Joints G5009 |  | 2024/19 | 2024-05-07 | MN30-F01 | 1 | 10 | 2 |  |  |  | RestartHold (Work Order) | M201 |  | M04 | 20000H Repl Driveshaft Uvsl Joints 16M
6042.10.02.61-GR002-DRIV | Drive G5009 | PHRN01 | 30732049 | 21140014 | 20000H Repl Final Drive RH G5009 | Repl Final Drive RH G5009 | 428732112 | 2018/24 | 2018-06-14 | SN43-G03 | 1 | 0.5 | 1 |  |  |  | RestartCompleted (Work Order) | M201 |  | M04 | 20000H Repl Final Drive RH 16M
6042.10.02.61-GR002-DRIV | Drive G5009 | PHRN01 | 30732050 | 21140015 | 14000H Repl Wheel & Brake Grup LHR G5009 | Repl Wheel & Brake Grp LHR G5009 | 428732116 | 2018/24 | 2018-06-14 | SN43-G03 | 1 | 0.5 | 1 |  |  |  | RestartCompleted (Work Order) | M201 |  | M04 | 14000H Repl Wheel & Brake Grup Rear 16M
6042.10.02.61-GR002-EICO | Elec Instrument & Ctrl Comp G5009 | PHRN01 | 30732090 | 21140100 | 10000H Ovhl Air Conditioner G5009 | Ovhl Air Conditioner G5009 | 427578958 | 2017/11 | 2017-03-16 | MN30-F03 | 1 | 10 | 1 |  |  |  | RestartCompleted (Work Order) | M201 |  | M03
6042.10.02.61-GR002-EICO | Elec Instrument & Ctrl Comp G5009 | PHRN01 | 30732058 | 21140063 | 20000H Repl Alternator G5009 | Repl Alternator G5009 | 427576183 | 2017/11 | 2017-03-17 | MN30-F03 | 1 | 10 | 1 |  |  |  | RestartCompleted (Work Order) | M201 |  | M04 | 8000H Repl Alternator
6042.10.02.61-GR002-EICO | Elec Instrument & Ctrl Comp G5009 | PHRN01 | 30732059 | 21140064 | 20000H Repl Starter Motor G5009 | Repl Starter Motor G5009 | 427578959 | 2017/11 | 2017-03-16 | MN30-F03 | 1 | 10 | 1 |  |  |  | RestartCompleted (Work Order) | M201 |  | M04 | 8000H Repl Starter Motor
6042.10.02.61-GR002-ENGI | Engine G5009 | PHRN01 | 30732067 | 21140074 | 20000H Ovhl Radiator G5009 | Ovhl Radiator G5009 | 427578729 | 2017/15 | 2017-04-13 | MN30-F03 | 2 | 10 | 1 |  |  |  | RestartCompleted (Work Order) | M201 |  | M04 | 20000H Ovhl Radiator 16M
6042.10.02.61-GR002-ENGI | Engine G5009 | PHRN01 | 30732063 | 21140070 | 20000H Repl Turbocharger G5009 | Repl Turbocharger G5009 | 427576180 | 2017/11 | 2017-03-17 | MN30-F03 | 1 | 6 | 1 |  |  |  | RestartCompleted (Work Order) | M201 |  | M04
6042.10.02.61-GR002-ENGI | Engine G5009 | PHRN01 | 30732061 | 21140067 | 20000H Repl Engine G5009 | Repl Engine G5009 | 428869692 | 2018/31 | 2018-08-02 | SN43-G03 | 1 | 0.5 | 4 |  |  |  | ScheduledCompleted (Work Order) | M201 |  | M04 | 20000H Repl Engine 16M
6042.10.02.61-GR002-HYSY | Hydraulic System G5009 | PHRN01 | 30732079 | 21140087 | 20000H Repl Circle Drive Box G5009 | Repl Circle Drive Box G5009 | 428958435 | 2018/35 | 2018-09-02 | SN43-G03 | 1 | 0.5 | 1 |  |  |  | RestartCompleted (Work Order) | M201 |  | M04 | 20000H Repl Circle Drive Box 16M
6042.10.02.61-GR002-HYSY | Hydraulic System G5009 | PHRN01 | 30732078 | 21140086 | 20000H Repl Center Shift Lock G5009 | Repl Center Shift Lock G5009 | 4202142176 | 2022/25 | 2022-06-26 | MN30-F01 | 1 | 5 | 2 |  |  |  | RestartCalled (Work Order) | M201 |  | M04 | 20000H Repl Center Shift Lock 16M
6042.10.02.61-GR002-HYSY | Hydraulic System G5009 | PHRN01 | 30732075 | 21140083 | 20000H Repl Motor Fan Drive G5009 | Repl Motor Fan Drive G5009 | 427578960 | 2017/10 | 2017-03-10 | MN30-F03 | 1 | 10 | 2 |  |  |  | ScheduledCompleted (Work Order) | M201 |  | M04
6042.10.02.61-GR002-HYSY | Hydraulic System G5009 | PHRN01 | 30732074 | 21140082 | 20000H Repl Pump Hydraulic Fan G5009 | Repl Pump Hydraulic Fan G5009 | 427578728 | 2017/11 | 2017-03-16 | MN30-F03 | 1 | 8 | 2 |  |  |  | RestartCompleted (Work Order) | M201 |  | M04 | 20000H Repl Hydraulic Fan Pump 16M
6042.10.02.61-GR002-HYSY | Hydraulic System G5009 | PHRN01 | 30732071 | 21140079 | 20000H Repl Pump Secondary Steer G5009 | Repl Pump Secondary Steering G5009 | 427578727 | 2017/11 | 2017-03-16 | MN30-F03 | 1 | 10 | 1 |  |  |  | RestartCompleted (Work Order) | M201 |  | M04 | 20000H Repl Secondary Steering Pump 16M
6042.10.02.61-GR002-HYSY | Hydraulic System G5009 | PHRN01 | 30732070 | 21140078 | 20000H Repl Pump Implement & Steer G5009 | Repl Pump Implement & Steer G5009 | 427578731 | 2017/11 | 2017-03-16 | MN30-F03 | 1 | 15 | 1 |  |  |  | RestartCompleted (Work Order) | M201 |  | M04 | 20000H Repl Implement Steering Pump 16M
6042.10.02.61-GR002-STRC | Structure G5009 | PHRN01 | 30732092 | 21140102 | 10000H Repl Operator Seat G5009 | Repl Operator Seat G5009 | 4202129731 | 2022/24 | 2022-06-18 | MN30-F01 | 1 | 6 | 4 |  |  |  | RestartCompleted (Work Order) | M201 |  | M04 | 10000H Repl Operator Seat 16M
6042.10.02.61-GR002-STRC | Structure G5009 | PHRN01 | 30732089 | 21140098 | 30000H Ovhl Ripper Frame G5009 | Ovhl Articulation G5009 |  | 2026/08 | 2026-02-17 | MN30-F01 | 1 | 20 | 2 |  |  |  | RestartHold (Work Order) | M201 |  | M04 | 30000H Ovhl Ripper Frame 16M
6042.10.02.61-GR002-STRC | Structure G5009 | PHRN01 | 30732089 | 21140097 | 30000H Ovhl Articulation G5009 | Ovhl Articulation G5009 | 4200817554 | 2020/12 | 2020-03-22 | MN30-F01 | 2 | 20 | 1 |  |  |  | RestartCompleted (Work Order) | M201 |  | M04
6042.10.02.61-GR004 | Grader Caterpillar 16M G5010 | PHRN01 | 30769585 | 21391729 | 500H Mech Svce & Lube Grader G5010 | Mech Svce & Lube Grader G5010 | 4200762484 | 2019/51 | 2019-12-21 | MN30-E01 | 1 | 10.5 | 96 |  |  |  | ScheduledCompleted (Work Order) | M201 |  | M03
6042.10.02.61-GR004 | Grader Caterpillar 16M G5010 | PHRN01 | 30769585 | 21391730 | 1000H Mech Svce & Lube Grader G5010 | Mech Svce & Lube Grader G5010 | 4200815326 | 2020/04 | 2020-01-25 | MN30-E01 | 1 | 10.5 | 98 |  |  |  | ScheduledCompleted (Work Order) | M201 |  | M03
6042.10.02.61-GR004 | Grader Caterpillar 16M G5010 | PHRN01 | 30769585 | 21391731 | 2000H Mech Svce & Lube Grader G5010 | Mech Svce & Lube Grader G5010 | 4201580719 | 2021/19 | 2021-05-15 | MN30-F01 | 1 | 1 | 126 |  |  |  | ScheduledCompleted (Work Order) | M201 |  | M03
6042.10.02.61-GR004 | Grader Caterpillar 16M G5010 | PHRN01 | 30797550 | 21249851 | 10000H Ovhl Grader Midlife G5010 | Ovhl Grader Midlife G5010 | 427777707 | 2017/13 | 2017-04-01 | MN30-SVC | 1 | 136 | 1 |  |  |  | RestartCompleted (Work Order) | M201 |  | M04
6042.10.02.61-GR004 | Grader Caterpillar 16M G5010 | TWKN01 | 30769627 | 21200046 | 6M Stat Audit Fire System QTEC G5010 | Stat Audit Fire Systems G5010 | 428016271 | 2017/30 | 2017-07-27 | MN30-F01 | 1 | 6 | 4 |  |  |  | ScheduledCompleted (Work Order) | M201 |  | M03 | 6M Stat Audit Fire System HYBRID 16M
6042.10.02.61-GR004 | Grader Caterpillar 16M G5010 | PHRN01 | 30769585 | 21200772 | 250H Mech Svce & Lube Grader G5010 | Mech Svce & Lube Grader G5010 | 426695502 | 2016/13 | 2016-04-02 | MN30-F01 | 1 | 15 | 14 |  |  |  | ScheduledCompleted (Work Order) | M201 |  | M03 | 250H Mech Svce & Lube 16M Grader R9H
6042.10.02.61-GR004 | Grader Caterpillar 16M G5010 | PHRN01 | 30770325 | 21201121 | 6000H Mech Calb Pilot Hydraulic G5010 | Calb Pilot Hydraulic G5010 | 4200542994 | 2020/36 | 2020-09-04 | MN30-F03 | 1 | 2 | 6 |  |  |  | RestartCompleted (Work Order) | M201 |  | M03
6042.10.02.61-GR004 | Grader Caterpillar 16M G5010 | PHRN01 | 30770314 | 21201108 | 4000H Calb Electronics G5010 | Calb Electronics G5010 | 426870690 | 2016/31 | 2016-08-04 | MN30-F01 | 1 | 6 | 1 |  |  |  | RestartCompleted (Work Order) | M201 |  | M03 | 4000H Calb Electronics
6042.10.02.61-GR004-DRIV | Drive G5010 | PHRN01 | 30770306 | 21201099 | 20000H Repl Final Drive RH G5010 | Repl Final Drive RH G5010 | 427628174 | 2018/31 | 2018-08-01 | MN30-F01 | 1 | 4 | 1 |  |  |  | RestartCompleted (Work Order) | M201 |  | M04
6042.10.02.61-GR004-DRIV | Drive G5010 | PHRN01 | 30770305 | 21201098 | 20000H Repl Axle Assembly Rear G5010 | Repl Axle Assembly Rear G5010 | 428646593 | 2018/19 | 2018-05-13 | SN43-G03 | 1 | 0.5 | 1 |  |  |  | RestartCompleted (Work Order) | M201 |  | M04 | 20000H Repl Axle Assembly Rear 16M
6042.10.02.61-GR004-DRIV | Drive G5010 | PHRN01 | 30796225 | 21248018 | 14000H Repl Wheel & Brake Grup RHF G5010 | Repl Wheel & Brake Grp RHF G5010 | 4200544708 | 2020/04 | 2020-01-20 | MN30-F03 | 2 | 12 | 2 |  |  |  | RestartCompleted (Work Order) | M201 |  | M04
6042.10.02.61-GR004-DRIV | Drive G5010 | PHRN01 | 30770304 | 21201097 | 14000H Repl Wheel & Brake Grup LHR G5010 | Repl Wheel & Brake Grp LHR G5010 | 4200384709 | 2019/37 | 2019-09-12 | SN43-G03 | 1 | 0.5 | 1 |  |  |  | RestartCompleted (Work Order) | M201 |  | M04 | 14000H Repl Wheel & Brake Grup Rear 16M
6042.10.02.61-GR004-DRIV | Drive G5010 | PHRN01 | 30770301 | 21201094 | 20000H Repl Transmission G5010 | Repl Transmission & Hoses G5010 | 427729398 | 2018/25 | 2018-06-19 | MN30-F01 | 2 | 60 | 2 |  |  |  | ScheduledCompleted (Work Order) | M201 |  | M04
6042.10.02.61-GR004-EICO | Elec Instrument & Ctrl Comp G5010 | PHRN01 | 30770316 | 21201110 | 20000H Repl Starter Motor G5010 | Repl Starter Motor G5010 | 427413141 | 2017/07 | 2017-02-17 | MN30-F03 | 1 | 10 | 1 |  |  |  | RestartCompleted (Work Order) | M201 |  | M04 | 8000H Repl Starter Motor
6042.10.02.61-GR004-EICO | Elec Instrument & Ctrl Comp G5010 | PHRN01 | 30770346 | 21201144 | 10000H Ovhl Air Conditioner G5010 | Ovhl Air Conditioner G5010 | 427413138 | 2017/07 | 2017-02-17 | MN30-F03 | 1 | 10.5 | 1 |  |  |  | RestartCompleted (Work Order) | M201 |  | M03 | 10000H Ovhl Air Conditioner 16M
6042.10.02.61-GR004-EICO | Elec Instrument & Ctrl Comp G5010 | PHRN01 | 30770315 | 21201109 | 20000H Repl Alternator G5010 | Repl Alternator G5010 | 4200544713 | 2019/48 | 2019-11-25 | MN30-F03 | 1 | 4 | 4 |  |  |  | RestartCompleted (Work Order) | M201 |  | M04 | 8000H Repl Alternator
6042.10.02.61-GR004-ENGI | Engine G5010 | PHRN01 | 30770323 | 21201118 | 20000H Ovhl Radiator G5010 | Ovhl Radiator G5010 | 428646592 | 2018/19 | 2018-05-13 | SN43-G03 | 1 | 0.5 | 1 |  |  |  | RestartCompleted (Work Order) | M201 |  | M04 | 20000H Ovhl Radiator 16M
6042.10.02.61-GR004-ENGI | Engine G5010 | PHRN01 | 30770317 | 21201111 | 20000H Repl Engine G5010 | Repl Engine G5010 | 428809096 | 2018/28 | 2018-07-12 | SN43-G03 | 1 | 0.5 | 2 |  |  |  | ScheduledCompleted (Work Order) | M201 |  | M04 | 20000H Repl Engine 16M
6042.10.02.61-GR004-HYSY | Hydraulic System G5010 | PHRN01 | 30770330 | 21201126 | 20000H Repl Circle Drive Box G5010 | Repl Circle Drive Box G5010 | 428646583 | 2018/19 | 2018-05-13 | SN43-G03 | 1 | 0.2 | 1 |  |  |  | RestartCompleted (Work Order) | M201 |  | M04 | 20000H Repl Circle Drive Box 16M
6042.10.02.61-GR004-HYSY | Hydraulic System G5010 | PHRN01 | 30770327 | 21201123 | 20000H Repl Motor Fan Drive G5010 | Repl Motor Fan Drive G5010 | 427413117 | 2017/07 | 2017-02-17 | MN30-F03 | 1 | 10 | 1 |  |  |  | RestartCompleted (Work Order) | M201 |  | M04
6042.10.02.61-GR004-HYSY | Hydraulic System G5010 | PHRN01 | 30770326 | 21201122 | 20000H Repl Pump Hydraulic Fan G5010 | Repl Pump Hydraulic Fan G5010 | 428795670 | 2018/27 | 2018-07-07 | SN43-G03 | 1 | 0.5 | 2 |  |  |  | RestartCompleted (Work Order) | M201 |  | M04 | 20000H Repl Hydraulic Fan Pump 16M
6042.10.02.61-GR004-STRC | Structure G5010 | PHRN01 | 30770345 | 21201141 | 30000H Ovhl Articulation G5010 | Ovhl Articulation G5010 | 428646625 | 2018/19 | 2018-05-13 | SN43-G03 | 1 | 0.5 | 1 |  |  |  | RestartCompleted (Work Order) | M201 |  | M04 | 30000H Repl Articulation 16M
6042.10.02.61-GR004-STRC | Structure G5010 | PHRN01 | 30770345 | 21201142 | 30000H Ovhl Ripper Frame G5010 | Ovhl Articulation G5010 | 4200545278 | 2020/12 | 2020-03-19 | MN30-F01 | 2 | 7 | 2 |  |  |  | RestartCompleted (Work Order) | M201 |  | M04
6042.10.02.61-GR005 | Grader Caterpillar 16M G5011 | TWKN01 | 30769628 | 21200047 | 6M Stat Audit Fire System QTEC G5011 | Stat Audit Fire Systems G5011 | 428055563 | 2017/32 | 2017-08-10 | MN30-F01 | 1 | 8 | 4 |  |  |  | ScheduledCompleted (Work Order) | M201 |  | M03 | 6M Stat Audit Fire System HYBRID 16M
6042.10.02.61-GR005 | Grader Caterpillar 16M G5011 | PHRN01 | 30769586 | 21391734 | 2000H Mech Svce & Lube Grader G5011 | Mech Svce & Lube Grader G5011 | 4200710737 | 2019/47 | 2019-11-23 | MN30-E01 | 1 | 10.5 | 96 |  |  |  | ScheduledCompleted (Work Order) | M201 |  | M03
6042.10.02.61-GR005 | Grader Caterpillar 16M G5011 | PHRN01 | 30769586 | 21200773 | 250H Mech Svce & Lube Grader G5011 | Mech Svce & Lube Grader G5011 | 426601011 | 2016/09 | 2016-03-01 | MN30-F01 | 2 | 20 | 12 |  |  |  | ScheduledCompleted (Work Order) | M201 |  | M03 | 250H Mech Svce & Lube 16M Grader R9H
6042.10.02.61-GR005 | Grader Caterpillar 16M G5011 | PHRN01 | 30797551 | 21249852 | 10000H Ovhl Grader Midlife G5011 | Ovhl Grader Midlife G5011 | 427777708 | 2017/13 | 2017-04-01 | SN43-G03 | 1 | 7 | 1 |  |  |  | RestartCompleted (Work Order) | M201 |  | M04 | 10000H Ovhl Grader Midlife 16M
6042.10.02.61-GR005 | Grader Caterpillar 16M G5011 | PHRN01 | 30770363 | 21201163 | 4000H Calb Electronics G5011 | Calb Electronics G5011 | 4200593131 | 2019/48 | 2019-11-29 | MN30-F03 | 1 | 2 | 8 |  |  |  | ScheduledCompleted (Work Order) | M201 |  | M03 | 4000H Calb Electronics
6042.10.02.61-GR005 | Grader Caterpillar 16M G5011 | PHRN01 | 30770374 | 21201176 | 6000H Mech Calb Pilot Hydraulic G5011 | Calb Pilot Hydraulic G5011 | 426886896 | 2016/31 | 2016-08-07 | MN30-E01 | 1 | 6 | 1 |  |  |  | RestartCompleted (Work Order) | M201 |  | M03
6042.10.02.61-GR005-DRIV | Drive G5011 | PHRN01 | 30770355 | 21201154 | 20000H Repl Final Drive RH G5011 | Repl Final Drive RH G5011 | 428589562 | 2018/17 | 2018-04-23 | SN43-G03 | 1 | 0.5 | 1 |  |  |  | RestartCompleted (Work Order) | M201 |  | M04 | 20000H Repl Final Drive RH 16M
6042.10.02.61-GR005-DRIV | Drive G5011 | PHRN01 | 30770354 | 21201153 | 20000H Repl Axle Assembly Rear G5011 | Repl Axle Assembly Rear G5011 | 428589572 | 2018/17 | 2018-04-23 | SN43-G03 | 1 | 0.5 | 1 |  |  |  | RestartCompleted (Work Order) | M201 |  | M04 | 20000H Repl Axle Assembly Rear 16M
6042.10.02.61-GR005-DRIV | Drive G5011 | PHRN01 | 30770353 | 21201152 | 14000H Repl Wheel & Brake Grup LHR G5011 | Repl Wheel & Brake Grp LHR G5011 | 428230457 | 2018/17 | 2018-04-25 | SN43-G03 | 1 | 0.5 | 1 |  |  |  | RestartCompleted (Work Order) | M201 |  | M04 | 14000H Repl Wheel & Brake Grup Rear 16M
6042.10.02.61-GR005-DRIV | Drive G5011 | PHRN01 | 30796229 | 21248022 | 14000H Repl Wheel & Brake Grup RHR G5011 | Repl Wheel & Brake Grp RHR G5011 | 428589648 | 2018/17 | 2018-04-23 | SN43-G03 | 1 | 0.5 | 1 |  |  |  | RestartCompleted (Work Order) | M201 |  | M04 | 14000H Repl Wheel & Brake Grup Rear 16M
6042.10.02.61-GR005-DRIV | Drive G5011 | PHRN01 | 30770350 | 21201149 | 20000H Repl Transmission G5011 | Repl Transmission & Hoses G5011 | 427777452 | 2018/15 | 2018-04-15 | SN43-G03 | 1 | 0.5 | 2 |  |  |  | ScheduledCompleted (Work Order) | M201 |  | M04 | 20000H Repl Transmission 16M
6042.10.02.61-GR005-DRIV | Drive G5011 | PHRN01 | 30796217 | 21248010 | 20000H Repl Final Drive LH G5011 | Repl Final Drive LH G5011 | 4201974615 | 2022/10 | 2022-03-10 | MN30-F02 | 1 | 4 | 2 |  |  |  | Cycle StartCompleted (Work Order) | M201 |  | M04
6042.10.02.61-GR005-DRIV | Drive G5011 | PHRN01 | 30895968 | 21433810 | 20000H Repl Axle Assembly Front G5011 | Repl Axle AssemblyFrontG5011 | 4201975154 | 2022/10 | 2022-03-10 | MN30-F02 | 1 | 3 | 1 |  |  |  | RestartCompleted (Work Order) | M201 |  | M04
6042.10.02.61-GR005-EICO | Elec Instrument & Ctrl Comp G5011 | PHRN01 | 30770395 | 21201199 | 10000H Ovhl Air Conditioner G5011 | Ovhl Air Conditioner G5011 | 4200387252 | 2019/37 | 2019-09-13 | MN30-F03 | 1 | 5 | 5 |  |  |  | ScheduledCompleted (Work Order) | M201 |  | M03 | 10000H Ovhl Air Conditioner 16M
6042.10.02.61-GR005-EICO | Elec Instrument & Ctrl Comp G5011 | PHRN01 | 30770365 | 21201165 | 20000H Repl Starter Motor G5011 | Repl Starter Motor G5011 | 4200454152 | 2019/41 | 2019-10-07 | MN30-F03 | 1 | 2 | 3 |  |  |  | ScheduledCompleted (Work Order) | M201 |  | M04 | 8000H Repl Starter Motor
6042.10.02.61-GR005-EICO | Elec Instrument & Ctrl Comp G5011 | PHRN01 | 30770364 | 21201164 | 20000H Repl Alternator G5011 | Repl Alternator G5011 | 427297747 | 2017/01 | 2017-01-06 | MN30-F03 | 1 | 10 | 1 |  |  |  | RestartCompleted (Work Order) | M201 |  | M04 | 8000H Repl Alternator
6042.10.02.61-GR005-ENGI | Engine G5011 | PHRN01 | 30854861 | 21359885 | 20000H Repl Fuel Injectors G5011 | Repl Fuel Injectors G5011 | 4200509073 | 2019/47 | 2019-11-21 | MN30-F03 | 1 | 1 | 1 |  |  |  | RestartCompleted (Work Order) | M201 |  | M04
6042.10.02.61-GR005-ENGI | Engine G5011 | PHRN01 | 30770372 | 21201173 | 20000H Ovhl Radiator G5011 | Ovhl Radiator G5011 | 428589537 | 2018/17 | 2018-04-23 | SN43-G03 | 1 | 0.5 | 1 |  |  |  | RestartCompleted (Work Order) | M201 |  | M04 | 20000H Ovhl Radiator 16M
6042.10.02.61-GR005-ENGI | Engine G5011 | PHRN01 | 30770366 | 21201166 | 20000H Repl Engine G5011 | Repl Engine G5011 | 428918942 | 2018/36 | 2018-09-05 | SN43-G03 | 1 | 0.5 | 2 |  |  |  | ScheduledCompleted (Work Order) | M201 |  | M04 | 20000H Repl Engine 16M
6042.10.02.61-GR005-HYSY | Hydraulic System G5011 | PHRN01 | 30770375 | 21201177 | 20000H Repl Pump Hydraulic Fan G5011 | Repl Pump Hydraulic Fan G5011 | 427297705 | 2017/01 | 2017-01-06 | MN30-F03 | 1 | 5 | 1 |  |  |  | RestartCompleted (Work Order) | M201 |  | M04 | 20000H Repl Hydraulic Fan Pump 16M
6042.10.02.61-GR005-HYSY | Hydraulic System G5011 | PHRN01 | 30770376 | 21201178 | 20000H Repl Motor Fan Drive G5011 | Repl Motor Fan Drive G5011 | 427297753 | 2017/01 | 2017-01-06 | MN30-F03 | 1 | 10 | 1 |  |  |  | RestartCompleted (Work Order) | M201 |  | M04
6042.10.02.61-GR005-HYSY | Hydraulic System G5011 | PHRN01 | 30770379 | 21201181 | 20000H Repl Circle Drive Box G5011 | Repl Circle Drive Box G5011 | 4200403106 | 2019/38 | 2019-09-19 | SN43-G03 | 1 | 0.5 | 1 |  |  |  | RestartCompleted (Work Order) | M201 |  | M04 | 20000H Repl Circle Drive Box 16M
6042.10.02.61-GR005-STRC | Structure G5011 | PHRN01 | 30770394 | 21201196 | 30000H Ovhl Articulation G5011 | Ovhl Articulation G5011 | 428589547 | 2018/17 | 2018-04-23 | SN43-G03 | 1 | 0.5 | 1 |  |  |  | RestartCompleted (Work Order) | M201 |  | M04 | 30000H Repl Articulation 16M
6042.10.02.61-GR006 | Grader Caterpillar 18M3 G5012 | PHRN01 | 30870594 | 21389740 | 2000H Mech Svce Grader G5012 | Mech Svce & Lube Grader G5012 | 4201226241 | 2021/11 | 2021-03-16 | MN30-F01 | 2 | 1 | 20 |  |  |  | ScheduledCompleted (Work Order) | M201 |  | M03
6042.10.02.61-GR006 | Grader Caterpillar 18M3 G5012 | PHRN01 | 30870594 | 21389738 | 500H Mech Svce Grader G5012 | Mech Svce & Lube Grader G5012 | 4201285202 | 2021/14 | 2021-04-11 | MN30-F01 | 1 | 0.5 | 21 |  |  |  | ScheduledCompleted (Work Order) | M201 |  | M03
6042.10.02.61-GR001 | Grader Caterpillar 16M G5008 | TMKN01 | 30906595 | 21450730 | 12M Mech Insp Equipment Fire G5008 | Mech Insp Equipment Fire G5008 |  | 2023/39 | 2023-09-25 | MN30-F07 | 1 | 8 | 1 | 12 |  |  | RestartHold (Work Order) | M201 |  | M03 | 12M Mech Insp Equi Fire 16M
6042.10.02.61-GR002 | Grader Caterpillar 16M G5009 | TMKN01 | 30906596 | 21450731 | 12M Mech Insp Equipment Fire G5009 | Mech Insp Equipment Fire G5009 |  | 2023/39 | 2023-09-25 | MN30-F07 | 1 | 8 | 1 | 12 |  |  | RestartHold (Work Order) | M201 |  | M03 | 12M Mech Insp Equi Fire 16M
6042.10.02.61-GR004 | Grader Caterpillar 16M G5010 | TMKN01 | 30906597 | 21450732 | 12M Mech Insp Equipment Fire G5010 | Mech Insp Equipment Fire G5010 |  | 2023/39 | 2023-09-26 | MN30-F07 | 1 | 8 | 1 | 12 |  |  | RestartHold (Work Order) | M201 |  | M03 | 12M Mech Insp Equi Fire 16M
6042.10.02.61-GR005 | Grader Caterpillar 16M G5011 | TMKN01 | 30906598 | 21450733 | 12M Mech Insp Equipment Fire G5011 | Mech Insp Equipment Fire G5011 |  | 2023/39 | 2023-09-27 | MN30-F07 | 1 | 8 | 1 | 12 |  |  | RestartHold (Work Order) | M201 |  | M03 | 12M Mech Insp Equi Fire 16M
6042.10.02.61-GR006 | Grader Caterpillar 18M3 G5012 | TMKN01 | 30906599 | 21450734 | 12M Mech Insp Equipment Fire G5012 | Mech Insp Equipment Fire G5012 |  | 2023/39 | 2023-09-28 | MN30-F07 | 1 | 8 | 1 | 12 |  |  | RestartHold (Work Order) | M201 |  | M03 | 12M Mech Insp Equi Fire 18M3
6042.10.02.61-GR001 | Grader Caterpillar 16M G5008 | PHRN01 | 30318190 | 21391704 | 500H Mech Svce & Lube Grader G5008 | Mech Svce & Lube Grader G5008 | 4200748120 | 2019/51 | 2019-12-17 | SN30-T01 | 1 | 1 | 78 | 14 |  |  | ScheduledCompleted (Work Order) | M201 |  | M03 | 500H Mech Svce & Lube Schedule 16M
6042.10.02.61-GR005 | Grader Caterpillar 16M G5011 | PHRN01 | 30769586 | 21391732 | 500H Mech Svce & Lube Grader G5011 | Mech Svce & Lube Grader G5011 | 4200479414 | 2019/33 | 2019-08-17 | SN30-T01 | 1 | 1 | 90 | 14 |  |  | ScheduledCompleted (Work Order) | M201 |  | M03 | 500H Mech Svce & Lube 16M Grader R9H
6042.10.02.61-GR001 | Grader Caterpillar 16M G5008 | PHRN01 | 30318190 | 21391705 | 1000H Mech Svce & Lube Grader G5008 | Mech Svce & Lube Grader G5008 | 4200588714 | 2019/39 | 2019-09-28 | MN30-F01 | 1 | 1 | 76 | 24 |  |  | ScheduledCompleted (Work Order) | M201 |  | M03 | 1000H Mech Svce & Lube Schedule 16M
6042.10.02.61-GR002 | Grader Caterpillar 16M G5009 | PHRN01 | 30317856 | 21391702 | 1000H Mech Svce & Lube Grader G5009 | Mech Svce & Lube Grader G5009 | 4200661016 | 2019/43 | 2019-10-25 | SN30-T01 | 1 | 1 | 119 | 24 |  |  | ScheduledCompleted (Work Order) | M201 |  | M03 | 1000H Mech Svce & Lube Schedule 16M
6042.10.02.61-GR005 | Grader Caterpillar 16M G5011 | PHRN01 | 30769586 | 21391733 | 1000H Mech Svce & Lube Grader G5011 | Mech Svce & Lube Grader G5011 | 4200571318 | 2019/38 | 2019-09-21 | SN30-T01 | 1 | 1 | 92 | 24 |  |  | ScheduledCompleted (Work Order) | M201 |  | M03 | 1000H Mech Svce & Lube 16M Grader R9H
6042.10.02.61-GR006 | Grader Caterpillar 18M3 G5012 | TWKN01 | 30870595 | 21389741 | 6M Stat Audit Fire System QTEC G5012 | Stat Audit Fire Systems G5012 | 4200989540 | 2020/18 | 2020-04-28 | MN30-F01 | 1 | 4 | 1 | 24 |  |  | RestartCompleted (Work Order) | M201 |  | M03 | 6M Stat Audit Fire Systems 18M3
6042.10.02.61-GR006 | Grader Caterpillar 18M3 G5012 | PHRN01 | 30870594 | 21389739 | 1000H Mech Svce Grader G5012 | Mech Svce & Lube Grader G5012 | 4200803803 | 2020/03 | 2020-01-14 | MN30-F01 | 1 | 1 | 4 | 24 |  |  | ScheduledCompleted (Work Order) | M201 |  | M03 | 1000H Mech Svce Grader 18M3
6042.10.02.61-GR001 | Grader Caterpillar 16M G5008 | PHRN01 | 30318190 | 21391706 | 2000H Mech Svce & Lube Grader G5008 | Mech Svce & Lube Grader G5008 | 4200938632 | 2020/14 | 2020-04-01 | MN30-F01 | 1 | 3 | 80 | 36 |  |  | ScheduledCompleted (Work Order) | M201 |  | M03 | 2000H Mech Svce & Lube Schedule 16M
6042.10.02.61-GR002 | Grader Caterpillar 16M G5009 | PHRN01 | 30317856 | 21391703 | 2000H Mech Svce & Lube Grader G5009 | Mech Svce & Lube Grader G5009 | 4200477670 | 2019/33 | 2019-08-17 | SN30-T01 | 1 | 1 | 115 | 36 |  |  | ScheduledCompleted (Work Order) | M201 |  | M03 | 2000H Mech Svce & Lube Schedule 16M
6042.10.02.61-GR001 | Grader Caterpillar 16M G5008 | TWKN01 | 30319873 | 21387905 | 12M Stat Audit Fire System QTEC G5008 | Stat Audit Fire Systems G5008 |  | 2021/02 | 2021-01-13 | MN30-F07 | 1 | 8 | 16 | 41 |  |  | ScheduledSkipped (Work Order) | M201 |  | M03 | 12M Stat Audit Fire System HYBRID 16M
6042.10.02.61-GR002 | Grader Caterpillar 16M G5009 | TWKN01 | 30319015 | 21387903 | 12M Stat Audit Fire System QTEC G5009 | Stat Audit Fire Systems G5009 |  | 2019/26 | 2019-06-27 | MN30-F07 | 1 | 8 | 12 | 41 |  |  | ScheduledCompleted (Work Order) | M201 |  | M03 | 12M Stat Audit Fire System HYBRID 16M
6042.10.02.61-GR004 | Grader Caterpillar 16M G5010 | TWKN01 | 30769627 | 21387907 | 12M Stat Audit Fire System QTEC G5010 | Stat Audit Fire Systems G5010 | 4201345137 | 2020/49 | 2020-12-02 | MN30-F01 | 1 | 8 | 12 | 41 |  |  | ScheduledCompleted (Work Order) | M201 |  | M03 | 12M Stat Audit Fire System QTEC 16M
6042.10.02.61-GR005 | Grader Caterpillar 16M G5011 | TWKN01 | 30769628 | 21387909 | 12M Stat Audit Fire System QTEC G5011 | Stat Audit Fire Systems G5011 | 4201664124 | 2021/25 | 2021-06-21 | MN30-F07 | 1 | 8 | 12 | 41 |  |  | ScheduledCompleted (Work Order) | M201 |  | M03 | 12M Stat Audit Fire System QTEC 16M
6042.10.02.61-GR006 | Grader Caterpillar 18M3 G5012 | TWKN01 | 30870595 | 21389742 | 12M Stat Audit Fire System QTEC G5012 | Stat Audit Fire Systems G5012 | 4201267903 | 2020/42 | 2020-10-13 | MN30-F07 | 1 | 8 | 2 | 41 |  |  | ScheduledCompleted (Work Order) | M201 |  | M03 | 12M Stat Audit Fire Systems 18M3
6042.10.02.61-GR001 | Grader Caterpillar 16M G5008 | PHRN01 | 30319683 | 20454733 | 4000H Mech Adju Engine Valve Set G5008 | Insp Adjust Valve Set G5008 | 423307733 | 2014/13 | 2014-03-26 | MN30-F07 | 1 | 10.5 | 1 | 57 |  |  | RestartCompleted (Work Order) | M201 |  | M03 | 4000H Mech Insp Adju Valve Set
6042.10.02.61-GR001 | Grader Caterpillar 16M G5008 | PHRN01 | 30318234 | 20452761 | 4000H Calb Electronics G5008 | Calb Electronics G5008 | 423307691 | 2014/13 | 2014-03-26 | MN30-F07 | 1 | 6 | 1 | 57 |  |  | RestartCompleted (Work Order) | M201 |  | M03 | 4000H Mech Calb Electronics
6042.10.02.61-GR001 | Grader Caterpillar 16M G5008 | PHRN01 | 30318190 | 21428136 | 4000H Mech Svce & Lube Grader G5008 | Mech Svce & Lube Grader G5008 | 4202247934 | 2022/26 | 2022-07-03 | SN30-T01 | 1 | 1 | 96 | 57 |  |  | ScheduledCompleted (Work Order) | M201 |  | M03 | 4000H Mech Svce & Lube Schedule 16M
6042.10.02.61-GR002 | Grader Caterpillar 16M G5009 | PHRN01 | 30732062 | 21140069 | 4000H Mech Adju Engine Valve Set G5009 | Insp Adjust Valve Set G5009 | 427576182 | 2017/11 | 2017-03-17 | MN30-F07 | 1 | 10.5 | 1 | 57 |  |  | RestartCompleted (Work Order) | M201 |  | M03 | 4000H Mech Insp Adju Valve Set
6042.10.02.61-GR002 | Grader Caterpillar 16M G5009 | PHRN01 | 30317856 | 21428137 | 4000H Mech Svce & Lube Grader G5009 | Mech Svce & Lube Grader G5009 | 4201917950 | 2021/48 | 2021-12-02 | MN30-F01 | 1 | 1 | 163 | 57 |  |  | ScheduledCompleted (Work Order) | M201 |  | M03 | 4000H Mech Svce & Lube Schedule 16M
6042.10.02.61-GR004 | Grader Caterpillar 16M G5010 | PHRN01 | 30769585 | 21428138 | 4000H Mech Svce & Lube Grader G5010 | Mech Svce & Lube Grader G5010 | 4202010837 | 2022/05 | 2022-02-02 | SN30-T01 | 1 | 1 | 142 | 57 |  |  | ScheduledCompleted (Work Order) | M201 |  | M03 | 4000H Mech Svce & Lube 16M Grader R9H
6042.10.02.61-GR004 | Grader Caterpillar 16M G5010 | PHRN01 | 30770318 | 21201113 | 4000H Mech Adju Engine Valve Set G5010 | Insp Adjust Valve Set G5010 | 426870686 | 2016/31 | 2016-08-04 | MN30-F07 | 1 | 6 | 1 | 57 |  |  | RestartCompleted (Work Order) | M201 |  | M03 | 4000H Mech Insp Adju Valve Set
6042.10.02.61-GR005 | Grader Caterpillar 16M G5011 | PHRN01 | 30769586 | 21428139 | 4000H Mech Svce & Lube Grader G5011 | Mech Svce & Lube Grader G5011 | 4201865682 | 2021/44 | 2021-11-01 | SN30-T01 | 1 | 1 | 136 | 57 |  |  | ScheduledCompleted (Work Order) | M201 |  | M03 | 4000H Mech Svce & Lube 16M Grader R9H
6042.10.02.61-GR005 | Grader Caterpillar 16M G5011 | PHRN01 | 30770367 | 21201168 | 4000H Mech Adju Engine Valve Set G5011 | Insp Adjust Valve Set G5011 | 4200514906 | 2019/47 | 2019-11-21 | MN30-F01 | 1 | 0.5 | 1 | 57 |  |  | RestartCompleted (Work Order) | M201 |  | M03 | 4000H Mech Insp Adju Valve Set
6042.10.02.61-GR006 | Grader Caterpillar 18M3 G5012 | PHRN01 | 30877423 | 21402745 | 4000H Mech Calb Electronics G5012 | Calb Electronics G5012 | 4201009287 | 2020/28 | 2020-07-09 | MN30-F07 | 1 | 6 | 1 | 57 |  |  | RestartCompleted (Work Order) | M201 |  | M03 | 4000H Mech Calb Electronics 18M3
6042.10.02.61-GR006 | Grader Caterpillar 18M3 G5012 | PHRN01 | 30877379 | 21402708 | 4000H Mech Adju Engine Valve Set G5012 | Repl Engine G5012 | 4201009288 | 2020/28 | 2020-07-09 | MN30-F01 | 1 | 10.5 | 1 | 57 |  |  | RestartCompleted (Work Order) | M201 |  | M03 | 4000H Mech Insp Adju Valve Set 18M3
6042.10.02.61-GR006 | Grader Caterpillar 18M3 G5012 | PHRN01 | 30870594 | 21428140 | 4000H Mech Svce Grader G5012 | Mech Svce & Lube Grader G5012 | 4202015033 | 2022/26 | 2022-06-30 | SN30-T01 | 1 | 1 | 36 | 57 |  |  | ScheduledCompleted (Work Order) | M201 |  | M03 | 4000H Mech Svce Grader 18M3
6042.10.02.61-GR001 | Grader Caterpillar 16M G5008 | PHRN01 | 30317883 | 20452166 | 6000H Calb Joystick G5008 | Calb Joystick G5008 | 4200856085 | 2020/07 | 2020-02-14 | MN30-E01 | 1 | 2 | 5 | 62 |  |  | RestartCompleted (Work Order) | M201 |  | M03 | 6000H Calb Joystick
6042.10.02.61-GR002 | Grader Caterpillar 16M G5009 | PHRN01 | 30732034 | 21140008 | 6000H Calb Joystick G5009 | Calb Joystick G5009 | 4200871702 | 2020/08 | 2020-02-23 | MN30-F01 | 1 | 6 | 1 | 62 |  |  | RestartCompleted (Work Order) | M201 |  | M03 | 6000H Calb Joystick
6042.10.02.61-GR004 | Grader Caterpillar 16M G5010 | PHRN01 | 30770300 | 21201092 | 6000H Calb Joystick G5010 | Calb Joystick G5010 | 426870688 | 2016/31 | 2016-08-04 | MN30-F01 | 1 | 6 | 1 | 62 |  |  | RestartCompleted (Work Order) | M201 |  | M03 | 6000H Calb Joystick
6042.10.02.61-GR005 | Grader Caterpillar 16M G5011 | PHRN01 | 30770349 | 21201147 | 6000H Calb Joystick G5011 | Calb Joystick G5011 | 4200514903 | 2019/47 | 2019-11-21 | MN30-F07 | 1 | 6 | 5 | 62 |  |  | RestartCompleted (Work Order) | M201 |  | M03 | 6000H Calb Joystick
6042.10.02.61-GR006 | Grader Caterpillar 18M3 G5012 | PHRN01 | 30877404 | 21402710 | 6000H Mech Calb Pilot Hydraulic G5012 | Calb Pilot Hydraulic G5012 | 4201296842 | 2020/44 | 2020-11-01 | MN30-F01 | 1 | 6 | 1 | 62 |  |  | RestartCompleted (Work Order) | M201 |  | M03 | 6000H Mech Calb Pilot Hydraulic 18M3
6042.10.02.61-GR006 | Grader Caterpillar 18M3 G5012 | PHRN01 | 30877403 | 21402709 | 6000H Mech Calb Joystick G5012 | Calb Joystick G5012 | 4201296841 | 2020/44 | 2020-11-01 | MN30-F01 | 1 | 6 | 1 | 62 |  |  | RestartCompleted (Work Order) | M201 |  | M03 | 6000H Mech Calb Joystick 18M3
6042.10.02.61-GR001 | Grader Caterpillar 16M G5008 | PHRN01 | 30757920 | 21182516 | 10000H Post Maint Fire Supp Insp G5008 | Post Maint Fire Supp Insp G5008 | 428939326 | 2018/34 | 2018-08-26 | MN30-F01 | 1 | 4 | 1 | 70 |  |  | RestartCompleted (Work Order) | M201 |  | M04 | 10000H Post Maint Fire Supp Insp 16M
6042.10.02.61-GR001-EICO | Elec Instrument & Ctrl Comp G5008 | PHRN01 | 30890747 | 21424380 | 10000H Ovhl Air Conditioner G5008 | Ovhl Air Conditioner G5008 | 4202899931 | 2024/03 | 2024-01-18 | MN30-F01 | 1 | 4 | 1 | 70 |  |  | Cycle StartCalled (Work Order) | M201 |  | M03 | 10000H Ovhl Air Conditioner 16M
6042.10.02.61-GR001-STRC | Structure G5008 | PHRN01 | 30318338 | 20452917 | 10000H Repl Operator Seat G5008 | Repl Operator Seat G5008 | 423523015 | 2014/18 | 2014-05-02 | MN30-F03 | 1 | 3 | 1 | 70 |  |  | RestartCompleted (Work Order) | M201 |  | M04 | 10000H Repl Operator Seat 16M
6042.10.02.61-GR002 | Grader Caterpillar 16M G5009 | PHRN01 | 30757921 | 21182517 | 10000H Post Maint Fire Supp Insp G5009 | Post Maint Fire Supp Insp G5009 | 427578962 | 2017/11 | 2017-03-16 | MN30-F01 | 1 | 4 | 1 | 70 |  |  | RestartCompleted (Work Order) | M201 |  | M04 | 10000H Post Maint Fire Supp Insp 16M
6042.10.02.61-GR004 | Grader Caterpillar 16M G5010 | PHRN01 | 30805041 | 21263875 | 10000H Post Maint Fire Supp Insp G5010 | Post Maint Fire Supp Insp G5010 | 428795711 | 2018/27 | 2018-07-07 | MN30-F01 | 1 | 4 | 1 | 70 |  |  | RestartCompleted (Work Order) | M201 |  | M04 | 10000H Post Maint Fire Supp Insp 16M
6042.10.02.61-GR004-DRIV | Drive G5010 | PHRN01 | 30770301 | 21201093 | 10000H Repl Powertrain Hoses G5010 | Repl Transmission & Hoses G5010 | 427413142 | 2017/07 | 2017-02-17 | MN30-F03 | 2 | 20 | 1 | 70 |  |  | RestartCompleted (Work Order) | M201 |  | M04 | 10000H Repl Powertrain Hoses 16M
6042.10.02.61-GR004-STRC | Structure G5010 | PHRN01 | 30770347 | 21201145 | 10000H Repl Operator Seat G5010 | Repl Operator Seat G5010 | 427413139 | 2017/07 | 2017-02-17 | MN30-F03 | 1 | 6 | 1 | 70 |  |  | RestartCompleted (Work Order) | M201 |  | M04 | 10000H Repl Operator Seat 16M
6042.10.02.61-GR005 | Grader Caterpillar 16M G5011 | PHRN01 | 30805042 | 21263876 | 10000H Post Maint Fire Supp Insp G5011 | Post Maint Fire Supp Insp G5011 | 428956513 | 2018/35 | 2018-09-01 | MN30-F01 | 1 | 4 | 1 | 70 |  |  | RestartCompleted (Work Order) | M201 |  | M04 | 10000H Post Maint Fire Supp Insp 16M
6042.10.02.61-GR005-DRIV | Drive G5011 | PHRN01 | 30770350 | 21201148 | 10000H Repl Powertrain Hoses G5011 | Repl Transmission & Hoses G5011 | 4201164388 | 2020/41 | 2020-10-09 | MN30-F01 | 2 | 20 | 6 | 70 |  |  | RestartCompleted (Work Order) | M201 |  | M04 | 10000H Repl Powertrain Hoses 16M
6042.10.02.61-GR005-STRC | Structure G5011 | PHRN01 | 30770396 | 21201200 | 10000H Repl Operator Seat G5011 | Repl Operator Seat G5011 | 427297755 | 2017/01 | 2017-01-06 | MN30-F03 | 1 | 6 | 1 | 70 |  |  | RestartCompleted (Work Order) | M201 |  | M04 | 10000H Repl Operator Seat 16M
6042.10.02.61-GR006 | Grader Caterpillar 18M3 G5012 | PHRN01 | 30877420 | 21402742 | 10000H Ovhl Grader Midlife G5012 | Ovhl Grader Midlife G5012 | 4201597875 | 2021/27 | 2021-07-09 | MN30-F01 | 2 | 10.5 | 1 | 70 |  |  | Cycle StartCompleted (Work Order) | M201 |  | M04 | 10000H Mech Ovhl Grader Midlife 18M3
6042.10.02.61-GR006-DRIV | Drive G5012 | PHRN01 | 30877380 | 21402720 | 10000H Repl Powertrain Hoses G5012 | Repl Transmission & Hoses G5012 | 4201597872 | 2021/27 | 2021-07-09 | MN30-F01 | 2 | 20 | 1 | 70 |  |  | Cycle StartCompleted (Work Order) | M201 |  | M04 | 10000H Repl Powertrain Hoses 18M3
6042.10.02.61-GR006-EICO | Elec Instrument & Ctrl Comp G5012 | PHRN01 | 30877407 | 21402746 | 10000H Ovhl Air Conditioner G5012 | Ovhl Air Conditioner G5012 | 4201964336 | 2022/09 | 2022-03-02 | MN30-E01 | 1 | 4 | 3 | 70 |  |  | Cycle StartCompleted (Work Order) | M201 |  | M03 | 10000H Ovhl Air Conditioner 18M3
6042.10.02.61-GR006-HYSY | Hydraulic System G5012 | PHRN01 | 30877395 | 21402700 | 10000H Repl Cylinder Steering RH G5012 | Repl Cylinder Steering RH G5012 | 4201597876 | 2021/27 | 2021-07-09 | MN30-F01 | 1 | 5 | 1 | 70 |  |  | Cycle StartCompleted (Work Order) | M201 |  | M04 | 10000H Repl Cylinder Steering RH 18M3
6042.10.02.61-GR006-HYSY | Hydraulic System G5012 | PHRN01 | 30877396 | 21402701 | 10000H Repl Cylinder Steering LH G5012 | Repl Cylinder Steering LH G5012 | 4201597873 | 2021/27 | 2021-07-09 | MN30-F01 | 1 | 5 | 1 | 70 |  |  | Cycle StartCompleted (Work Order) | M201 |  | M04 | 10000H Repl Cylinder Steering LH 18M3
6042.10.02.61-GR006-STRC | Structure G5012 | PHRN01 | 30877411 | 21402722 | 10000H Repl Operator Seat G5012 | Repl Operator Seat G5012 | 4201597874 | 2021/27 | 2021-07-09 | MN30-F01 | 1 | 6 | 1 | 70 |  |  | Cycle StartCompleted (Work Order) | M201 |  | M04 | 10000H Repl Operator Seat 18M3
6042.10.02.61-GR001-DRIV | Drive G5008 | PHRN01 | 30796220 | 21248013 | 14000H Repl Wheel & Brake Grup RHR G5008 | Repl Wheel & Brake Grp RHR G5008 | 4201791689 | 2021/33 | 2021-08-19 | MN30-F02 | 1 | 1 | 1 | 74 |  |  | RestartCompleted (Work Order) | M201 |  | M04 | 14000H Repl Wheel & Brake Grup Rear 16M
6042.10.02.61-GR001-DRIV | Drive G5008 | PHRN01 | 30796219 | 21248012 | 14000H Repl Wheel & Brake Grup RHF G5008 | Repl Wheel & Brake Grp RHF G5008 | 4201791690 | 2021/33 | 2021-08-19 | MN30-F02 | 1 | 1 | 1 | 74 |  |  | RestartCompleted (Work Order) | M201 |  | M04 | 14000H Repl Wheel & Brake Grup Front 16M
6042.10.02.61-GR001-DRIV | Drive G5008 | PHRN01 | 30796218 | 21248011 | 14000H Repl Wheel & Brake Grup LHF G5008 | Repl Wheel & Brake Grp LHF G5008 | 4202268159 | 2022/37 | 2022-09-13 | MN30-F02 | 1 | 1 | 1 | 74 |  |  | RestartCompleted (Work Order) | M201 |  | M04 | 14000H Repl Wheel & Brake Grup Front 16M
6042.10.02.61-GR002-DRIV | Drive G5009 | PHRN01 | 30796221 | 21248014 | 14000H Repl Wheel & Brake Grup LHF G5009 | Repl Wheel & Brake Grp LHF G5009 | 428732121 | 2018/24 | 2018-06-14 | MN30-F02 | 1 | 2 | 1 | 74 |  |  | RestartCompleted (Work Order) | M201 |  | M04 | 14000H Repl Wheel & Brake Grup Front 16M
6042.10.02.61-GR004-DRIV | Drive G5010 | PHRN01 | 30796226 | 21248019 | 14000H Repl Wheel & Brake Grup RHR G5010 | Repl Wheel & Brake Grp RHR G5010 | 4201836045 | 2021/49 | 2021-12-08 | MN30-F02 | 1 | 1 | 1 | 74 |  |  | RestartCompleted (Work Order) | M201 |  | M04 | 14000H Repl Wheel & Brake Grup Rear 16M
6042.10.02.61-GR004-DRIV | Drive G5010 | PHRN01 | 30796224 | 21248017 | 14000H Repl Wheel & Brake Grup LHF G5010 | Repl Wheel & Brake Grp LHF G5010 | 4200384714 | 2019/37 | 2019-09-12 | MN30-F02 | 1 | 2 | 1 | 74 |  |  | RestartCompleted (Work Order) | M201 |  | M04 | 14000H Repl Wheel & Brake Grup Front 16M
6042.10.02.61-GR005-DRIV | Drive G5011 | PHRN01 | 30796227 | 21248020 | 14000H Repl Wheel & Brake Grup LHF G5011 | Repl Wheel & Brake Grp LHF G5011 | 428230578 | 2018/17 | 2018-04-25 | MN30-F01 | 2 | 5 | 1 | 74 |  |  | RestartCompleted (Work Order) | M201 |  | M04 | 14000H Repl Wheel & Brake Grup Front 16M
6042.10.02.61-GR005-DRIV | Drive G5011 | PHRN01 | 30796228 | 21248021 | 14000H Repl Wheel & Brake Grup RHF G5011 | Repl Wheel & Brake Grp RHF G5011 | 428589631 | 2018/17 | 2018-04-23 | MN30-F02 | 1 | 2 | 1 | 74 |  |  | RestartCompleted (Work Order) | M201 |  | M04 | 14000H Repl Wheel & Brake Grup Front 16M
6042.10.02.61-GR001-DRIV | Drive G5008 | PHRN01 | 30895955 | 21433807 | 20000H Repl Axle Assembly Front G5008 | Repl Axle AssemblyFrontG5008 |  | 2024/23 | 2024-06-09 | MN30-F01 | 2 | 10 | 1 | 80 |  |  | RestartHold (Work Order) | M201 |  | M04 | 20000H Repl Axle Assembly Front 16M
6042.10.02.61-GR001-DRIV | Drive G5008 | PHRN01 | 30317632 | 20451736 | 20000H Repl Driveshaft Uvsl G5008 | Repl Driveshaft Uvsl Joints G5008 | 425775440 | 2015/21 | 2015-05-19 | MN30-F03 | 1 | 10 | 1 | 80 |  |  | RestartCompleted (Work Order) | M201 |  | M04 | 20000H Repl Driveshaft Uvsl Joints 16M
6042.10.02.61-GR001-DRIV | Drive G5008 | PHRN01 | 30317207 | 20451123 | 20000H Repl Final Drive RH G5008 | Repl Final Drive RH G5008 | 425775439 | 2015/21 | 2015-05-19 | MN30-F03 | 2 | 20 | 1 | 80 |  |  | RestartCompleted (Work Order) | M201 |  | M04 | 20000H Repl Final Drive RH 16M
6042.10.02.61-GR001-DRIV | Drive G5008 | PHRN01 | 30796214 | 21248007 | 20000H Repl Final Drive LH G5008 | Repl Final Drive LH G5008 |  | 2024/23 | 2024-06-09 | MN30-F02 | 1 | 4 | 1 | 80 |  |  | Cycle StartHold (Work Order) | M201 |  | M04 | 20000H Repl Final Drive LH 16M
6042.10.02.61-GR001-EICO | Elec Instrument & Ctrl Comp G5008 | PHRN01 | 30890747 | 21424381 | 20000H Ovhl Air Conditioner G5008 | Ovhl Air Conditioner G5008 |  | 2026/46 | 2026-11-09 | MN30-F01 | 1 | 10 | 2 | 80 |  |  | ScheduledHold (Work Order) | M201 |  | M04 | 20000H Ovhl Air Conditioner 16M
6042.10.02.61-GR001-HYSY | Hydraulic System G5008 | PHRN01 | 30318456 | 20453089 | 20000H Repl Center Shift Lock G5008 | Repl Center Shift Lock G5008 | 424815183 | 2014/50 | 2014-12-09 | MN30-F03 | 2 | 10 | 1 | 80 |  |  | RestartCompleted (Work Order) | M201 |  | M04 | 20000H Repl Center Shift Lock 16M
6042.10.02.61-GR001-HYSY | Hydraulic System G5008 | PHRN01 | 30317882 | 20452165 | 20000H Repl Pump Implement & Steer G5008 | Repl Pump Implement & Steer G5008 | 423530708 | 2014/19 | 2014-05-05 | MN30-F03 | 1 | 15 | 1 | 80 |  |  | RestartCompleted (Work Order) | M201 |  | M04 | 20000H Repl Implement Steering Pump 16M
6042.10.02.61-GR001-HYSY | Hydraulic System G5008 | PHRN01 | 30317068 | 20450934 | 20000H Repl Circle Drive Box G5008 | Repl Circle Drive Box G5008 | 425763693 | 2015/22 | 2015-05-25 | MN30-F03 | 2 | 10 | 1 | 80 |  |  | RestartCompleted (Work Order) | M201 |  | M04 | 20000H Repl Circle Drive Box 16M
6042.10.02.61-GR002-DRIV | Drive G5009 | PHRN01 | 30895956 | 21433808 | 20000H Repl Axle Assembly Front G5009 | Repl Axle AssemblyFrontG5009 |  | 2024/15 | 2024-04-12 | MN30-F01 | 2 | 10 | 1 | 80 |  |  | RestartHold (Work Order) | M201 |  | M04 | 20000H Repl Axle Assembly Front 16M
6042.10.02.61-GR002-DRIV | Drive G5009 | PHRN01 | 30796215 | 21248008 | 20000H Repl Final Drive LH G5009 | Repl Final Drive LH G5009 | 428732120 | 2018/24 | 2018-06-14 | MN30-F02 | 1 | 4 | 1 | 80 |  |  | RestartCompleted (Work Order) | M201 |  | M04 | 20000H Repl Final Drive LH 16M
6042.10.02.61-GR002-EICO | Elec Instrument & Ctrl Comp G5009 | PHRN01 | 30732090 | 21391751 | 20000H Ovhl Air Conditioner G5009 | Ovhl Air Conditioner G5009 | 4200814324 | 2020/12 | 2020-03-20 | MN30-E01 | 1 | 10 | 5 | 80 |  |  | Cycle StartCompleted (Work Order) | M201 |  | M04 | 20000H Ovhl Air Conditioner 16M
6042.10.02.61-GR002-ENGI | Engine G5009 | PHRN01 | 30854859 | 21359883 | 20000H Repl Fuel Injectors G5009 | Repl Fuel Injectors G5009 | 4200766385 | 2020/08 | 2020-02-21 | MN30-F01 | 1 | 10.5 | 1 | 80 |  |  | RestartCompleted (Work Order) | M201 |  | M04 | 20000H Repl Fuel Injectors 16M
6042.10.02.61-GR004-DRIV | Drive G5010 | PHRN01 | 30796216 | 21248009 | 20000H Repl Final Drive LH G5010 | Repl Final Drive LH G5010 | 428646706 | 2018/19 | 2018-05-13 | MN30-F02 | 1 | 4 | 1 | 80 |  |  | RestartCompleted (Work Order) | M201 |  | M04 | 20000H Repl Final Drive LH 16M
6042.10.02.61-GR004-DRIV | Drive G5010 | PHRN01 | 30895967 | 21433809 | 20000H Repl Axle Assembly Front G5010 | Repl Axle AssemblyFrontG5010 |  | 2024/06 | 2024-02-07 | MN30-F01 | 2 | 10 | 1 | 80 |  |  | RestartHold (Work Order) | M201 |  | M04 | 20000H Repl Axle Assembly Front 16M
6042.10.02.61-GR004-DRIV | Drive G5010 | PHRN01 | 30770303 | 21201096 | 20000H Repl Driveshaft Uvsl G5010 | Repl Driveshaft Uvsl Joints G5010 | 4200534777 | 2019/47 | 2019-11-24 | MN30-F03 | 1 | 8 | 1 | 80 |  |  | RestartCompleted (Work Order) | M201 |  | M04 | 20000H Repl Driveshaft Uvsl Joints 16M
6042.10.02.61-GR004-EICO | Elec Instrument & Ctrl Comp G5010 | PHRN01 | 30770346 | 21391752 | 20000H Ovhl Air Conditioner G5010 | Ovhl Air Conditioner G5010 | 4200630534 | 2019/50 | 2019-12-12 | MN30-F03 | 1 | 10 | 7 | 80 |  |  | ScheduledCompleted (Work Order) | M201 |  | M04 | 20000H Ovhl Air Conditioner 16M
6042.10.02.61-GR004-ENGI | Engine G5010 | PHRN01 | 30770319 | 21201114 | 20000H Repl Turbocharger G5010 | Repl Turbocharger G5010 | 427413140 | 2017/07 | 2017-02-17 | MN30-F03 | 2 | 15 | 1 | 80 |  |  | RestartCompleted (Work Order) | M201 |  | M04 | 20000H Repl Turbocharger 16M
6042.10.02.61-GR004-ENGI | Engine G5010 | PHRN01 | 30854860 | 21359884 | 20000H Repl Fuel Injectors G5010 | Repl Fuel Injectors G5010 | 4200545411 | 2019/47 | 2019-11-23 | MN30-F03 | 1 | 10.5 | 1 | 80 |  |  | RestartCompleted (Work Order) | M201 |  | M04 | 20000H Repl Fuel Injectors 16M
6042.10.02.61-GR004-HYSY | Hydraulic System G5010 | PHRN01 | 30770333 | 21201129 | 20000H Repl Pump Secondary Steer G5010 | Repl Pump Secondary Steering G5010 | 4201969981 | 2022/09 | 2022-03-06 | MN30-F01 | 1 | 10 | 4 | 80 |  |  | Cycle StartCompleted (Work Order) | M201 |  | M04 | 20000H Repl Secondary Steering Pump 16M
6042.10.02.61-GR004-HYSY | Hydraulic System G5010 | PHRN01 | 30770332 | 21201128 | 20000H Repl Pump Implement & Steer G5010 | Repl Pump Implement & Steer G5010 | 4200448400 | 2019/40 | 2019-10-05 | MN30-F03 | 1 | 15 | 3 | 80 |  |  | ScheduledCompleted (Work Order) | M201 |  | M04 | 20000H Repl Implement Steering Pump 16M
6042.10.02.61-GR004-HYSY | Hydraulic System G5010 | PHRN01 | 30770329 | 21201125 | 20000H Repl Center Shift Lock G5010 | Repl Center Shift Lock G5010 | 4201709583 | 2021/37 | 2021-09-18 | MN30-F03 | 2 | 10 | 2 | 80 |  |  | Cycle StartCompleted (Work Order) | M201 |  | M04 | 20000H Repl Center Shift Lock 16M
6042.10.02.61-GR005-DRIV | Drive G5011 | PHRN01 | 30770352 | 21201151 | 20000H Repl Driveshaft Uvsl G5011 | Repl Driveshaft Uvsl Joints G5011 | 4200514912 | 2019/47 | 2019-11-21 | MN30-F03 | 1 | 10 | 1 | 80 |  |  | RestartCompleted (Work Order) | M201 |  | M04 | 20000H Repl Driveshaft Uvsl Joints 16M
6042.10.02.61-GR005-EICO | Elec Instrument & Ctrl Comp G5011 | PHRN01 | 30770395 | 21391753 | 20000H Ovhl Air Conditioner G5011 | Ovhl Air Conditioner G5011 |  | 2024/27 | 2024-07-06 | MN30-F01 | 1 | 10 | 9 | 80 |  |  | ScheduledHold (Work Order) | M201 |  | M04 | 20000H Ovhl Air Conditioner 16M
6042.10.02.61-GR005-ENGI | Engine G5011 | PHRN01 | 30770368 | 21201169 | 20000H Repl Turbocharger G5011 | Repl Turbocharger G5011 | 427297712 | 2017/01 | 2017-01-06 | MN30-F03 | 2 | 15 | 1 | 80 |  |  | RestartCompleted (Work Order) | M201 |  | M04 | 20000H Repl Turbocharger 16M
6042.10.02.61-GR005-HYSY | Hydraulic System G5011 | PHRN01 | 30770382 | 21201184 | 20000H Repl Pump Secondary Steer G5011 | Repl Pump Secondary Steering G5011 | 427297706 | 2017/01 | 2017-01-06 | MN30-F03 | 1 | 10 | 1 | 80 |  |  | RestartCompleted (Work Order) | M201 |  | M04 | 20000H Repl Secondary Steering Pump 16M
6042.10.02.61-GR005-HYSY | Hydraulic System G5011 | PHRN01 | 30770381 | 21201183 | 20000H Repl Pump Implement & Steer G5011 | Repl Pump Implement & Steer G5011 | 427297738 | 2017/01 | 2017-01-06 | MN30-F03 | 1 | 15 | 1 | 80 |  |  | RestartCompleted (Work Order) | M201 |  | M04 | 20000H Repl Implement Steering Pump 16M
6042.10.02.61-GR005-HYSY | Hydraulic System G5011 | PHRN01 | 30770378 | 21201180 | 20000H Repl Center Shift Lock G5011 | Repl Center Shift Lock G5011 | 428589538 | 2018/17 | 2018-04-23 | MN30-F03 | 2 | 10 | 1 | 80 |  |  | RestartCompleted (Work Order) | M201 |  | M04 | 20000H Repl Center Shift Lock 16M
6042.10.02.61-GR006-DRIV | Drive G5012 | PHRN01 | 30890507 | 21424158 | 20000H Repl Driveshaft Uvsl G5012 | Repl Driveshaft Uvsl Joints G5012 | 4202691429 | 2023/23 | 2023-06-11 | MN30-F01 | 1 | 10 | 1 | 80 |  |  | Cycle StartCalled (Work Order) | M201 |  | M04 | 20000H Repl Driveshaft Uvsl Joints 18M3
6042.10.02.61-GR006-DRIV | Drive G5012 | PHRN01 | 30877380 | 21402688 | 20000H Repl Transmission G5012 | Repl Transmission & Hoses G5012 | 4202691408 | 2023/23 | 2023-06-11 | MN30-F01 | 2 | 35 | 2 | 80 |  |  | ScheduledCalled (Work Order) | M201 |  | M04 | 20000H Repl Transmission 18M3
6042.10.02.61-GR006-DRIV | Drive G5012 | PHRN01 | 30877381 | 21402689 | 20000H Repl Axle Assembly Rear G5012 | Repl Axle Assembly Rear G5012 | 4202691409 | 2023/23 | 2023-06-11 | MN30-F02 | 1 | 4 | 1 | 80 |  |  | Cycle StartCalled (Work Order) | M201 |  | M04 | 20000H Repl Axle Assembly Rear 18M3
6042.10.02.61-GR006-DRIV | Drive G5012 | PHRN01 | 30877386 | 21402694 | 20000H Repl Final Drive RH G5012 | Repl Final Drive RH G5012 | 4202691413 | 2023/23 | 2023-06-11 | MN30-F02 | 1 | 4 | 1 | 80 |  |  | Cycle StartCalled (Work Order) | M201 |  | M04 | 20000H Repl Final Drive 18M3
6042.10.02.61-GR006-DRIV | Drive G5012 | PHRN01 | 30877387 | 21402738 | 20000H Repl Final Drive LH G5012 | Repl Final Drive LH G5012 | 4202691414 | 2023/23 | 2023-06-11 | MN30-F02 | 1 | 4 | 1 | 80 |  |  | Cycle StartCalled (Work Order) | M201 |  | M04 | 20000H Repl Final Drive 18M3
6042.10.02.61-GR006-DRIV | Drive G5012 | PHRN01 | 30877388 | 21402739 | 20000H Repl Wheel & Brake Grup LHF G5012 | Repl Wheel & Brake Group LHF G5012 | 4202691415 | 2023/23 | 2023-06-11 | MN30-F02 | 1 | 1 | 1 | 80 |  |  | Cycle StartCalled (Work Order) | M201 |  | M04 | 20000H Repl Wheel & Brake Group F 18M3
6042.10.02.61-GR006-DRIV | Drive G5012 | PHRN01 | 30877389 | 21402740 | 20000H Repl Wheel & Brake Grup RHF G5012 | Repl Wheel & Brake Group RHF G5012 | 4202691416 | 2023/23 | 2023-06-11 | MN30-F02 | 1 | 1 | 1 | 80 |  |  | Cycle StartCalled (Work Order) | M201 |  | M04 | 20000H Repl Wheel & Brake Group F 18M3
6042.10.02.61-GR006-DRIV | Drive G5012 | PHRN01 | 30877390 | 21402695 | 20000H Repl Wheel & Brake Grup LHR G5012 | Repl Wheel & Brake Group LHR G5012 | 4202691417 | 2023/23 | 2023-06-11 | MN30-F02 | 1 | 1 | 1 | 80 |  |  | Cycle StartCalled (Work Order) | M201 |  | M04 | 20000H Repl Wheel & Brake Group R 18M3
6042.10.02.61-GR006-DRIV | Drive G5012 | PHRN01 | 30877391 | 21402696 | 20000H Repl Wheel & Brake Grup RHR G5012 | Repl Wheel & Brake Group RHR G5012 | 4202691418 | 2023/23 | 2023-06-11 | MN30-F02 | 1 | 1 | 1 | 80 |  |  | Cycle StartCalled (Work Order) | M201 |  | M04 | 20000H Repl Wheel & Brake Group R 18M3
6042.10.02.61-GR006-EICO | Elec Instrument & Ctrl Comp G5012 | PHRN01 | 30877407 | 21402721 | 20000H Ovhl Air Conditioner G5012 | Ovhl Air Conditioner G5012 |  | 2024/08 | 2024-02-19 | MN30-F01 | 1 | 10 | 4 | 80 |  |  | ScheduledHold (Work Order) | M201 |  | M04 | 20000H Ovhl Air Conditioner 18M3
6042.10.02.61-GR006-EICO | Elec Instrument & Ctrl Comp G5012 | PHRN01 | 30890448 | 21424059 | 20000H Repl Starter Motors G5012 | Repl Starter Motor G5012 | 4202691427 | 2023/23 | 2023-06-11 | MN30-F01 | 1 | 10 | 1 | 80 |  |  | Cycle StartCalled (Work Order) | M201 |  | M04 | 20000H Repl Starter Motor 18M3
6042.10.02.61-GR006-EICO | Elec Instrument & Ctrl Comp G5012 | PHRN01 | 30890447 | 21424058 | 20000H Repl Alternator G5012 | Repl Alternator G5012 | 4202691426 | 2023/23 | 2023-06-11 | MN30-F01 | 1 | 10 | 1 | 80 |  |  | Cycle StartCalled (Work Order) | M201 |  | M04 | 20000H Repl Alternator 18M3
6042.10.02.61-GR006-ENGI | Engine G5012 | PHRN01 | 30877379 | 21402687 | 20000H Repl Engine G5012 | Repl Engine G5012 | 4202691407 | 2023/23 | 2023-06-11 | MN30-F01 | 2 | 30 | 5 | 80 |  |  | ScheduledCalled (Work Order) | M201 |  | M04 | 20000H Repl Engine 18M3
6042.10.02.61-GR006-ENGI | Engine G5012 | PHRN01 | 30890449 | 21424060 | 20000H Repl Turbocharger G5012 | Repl Turbocharger G5012 | 4202691428 | 2023/23 | 2023-06-11 | MN30-F01 | 2 | 15 | 1 | 80 |  |  | Cycle StartCalled (Work Order) | M201 |  | M04 | 20000H Repl Turbocharger 18M3
6042.10.02.61-GR006-ENGI | Engine G5012 | PHRN01 | 30877425 | 21402724 | 20000H Repl Radiator G5012 | Ovhl Radiator G5012 | 4202691425 | 2023/23 | 2023-06-11 | MN30-F01 | 2 | 10 | 1 | 80 |  |  | Cycle StartCalled (Work Order) | M201 |  | M04 | 20000H Repl Radiator 18M3
6042.10.02.61-GR006-ENGI | Engine G5012 | PHRN01 | 30877424 | 21402741 | 20000H Repl Fuel Injectors G5012 | Repl Fuel Injectors G5012 | 4202691424 | 2023/23 | 2023-06-11 | MN30-F01 | 2 | 10.5 | 1 | 80 |  |  | Cycle StartCalled (Work Order) | M201 |  | M04 | 20000H Repl Fuel Injectors 18M3
6042.10.02.61-GR006-HYSY | Hydraulic System G5012 | PHRN01 | 30877409 | 21402726 | 20000H Repl Circle Drive Box G5012 | Repl Circle Drive Box G5012 |  | 2025/23 | 2025-06-03 | MN30-F01 | 2 | 10 | 1 | 80 |  |  | RestartHold (Work Order) | M201 |  | M04 | 20000H Repl Circle Drive Box 18M3
6042.10.02.61-GR006-HYSY | Hydraulic System G5012 | PHRN01 | 30877384 | 21402692 | 20000H Repl Pump Secondary Steer G5012 | Repl Pump Secondary Steering G5012 | 4202691412 | 2023/23 | 2023-06-11 | MN30-F01 | 1 | 10 | 1 | 80 |  |  | Cycle StartCalled (Work Order) | M201 |  | M04 | 20000H Repl Pump Secondary Steering 18M3
6042.10.02.61-GR006-HYSY | Hydraulic System G5012 | PHRN01 | 30877383 | 21402691 | 20000H Repl Pump Hydraulic Fan G5012 | Repl Pump Hydraulic Fan G5012 | 4202691411 | 2023/23 | 2023-06-11 | MN30-F01 | 1 | 5 | 1 | 80 |  |  | Cycle StartCalled (Work Order) | M201 |  | M04 | 20000H Repl Pump Hydr Brake Fan 18M3
6042.10.02.61-GR006-HYSY | Hydraulic System G5012 | PHRN01 | 30877382 | 21402690 | 20000H Repl Pump Implement & Steer G5012 | Repl Pump Implement & Steering G5012 | 4202691410 | 2023/23 | 2023-06-11 | MN30-F01 | 1 | 15 | 1 | 80 |  |  | Cycle StartCalled (Work Order) | M201 |  | M04 | 20000H Repl Pump Implement & Steer 18M3
6042.10.02.61-GR006-HYSY | Hydraulic System G5012 | PHRN01 | 30877406 | 21402717 | 20000H Repl Motor Fan Drive G5012 | Repl Motor Fan Drive G5012 | 4202691420 | 2023/23 | 2023-06-11 | MN30-F01 | 1 | 10 | 1 | 80 |  |  | Cycle StartCalled (Work Order) | M201 |  | M04 | 20000H Repl Motor Fan Drive 18M3
6042.10.02.61-GR006-HYSY | Hydraulic System G5012 | PHRN01 | 30877402 | 21402707 | 20000H Repl Circle Drive Motor G5012 | Repl Circle Drive Motor G5012 | 4202691419 | 2023/23 | 2023-06-11 | MN30-F01 | 1 | 5 | 1 | 80 |  |  | Cycle StartCompleted (Work Order) | M201 |  | M04 | 20000H Repl Motor Circle Drive 18M3
6042.10.02.61-GR006-STRC | Structure G5012 | PHRN01 | 30877422 | 21402744 | 20000H Repl Spindle RHF G5012 | Repl Spindle RHF G5012 | 4202691423 | 2023/23 | 2023-06-11 | MN30-F01 | 2 | 6 | 1 | 80 |  |  | Cycle StartCalled (Work Order) | M201 |  | M04 | 20000H Repl Spindle Front 18M3
6042.10.02.61-GR006-STRC | Structure G5012 | PHRN01 | 30877421 | 21402743 | 20000H Repl Spindle LHF G5012 | Repl Spindle LHF G5012 | 4202691422 | 2023/23 | 2023-06-11 | MN30-F01 | 2 | 6 | 1 | 80 |  |  | Cycle StartCalled (Work Order) | M201 |  | M04 | 20000H Repl Spindle Front 18M3
6042.10.02.61-GR006-STRC | Structure G5012 | PHRN01 | 30877408 | 21402725 | 20000H Repl Centre Shift Lock G5012 | Repl Center Shift Lock G5012 | 4202691421 | 2023/23 | 2023-06-11 | MN30-F01 | 1 | 1 | 1 | 80 |  |  | Cycle StartCalled (Work Order) | M201 |  | M04 | 20000H Repl Centre Shift Lock 18M3
6042.10.02.61-GR001-STRC | Structure G5008 | PHRN01 | 30319146 | 20454033 | 30000H Ovhl Articulation G5008 | Ovhl Articulation G5008 | 426194599 | 2015/38 | 2015-09-16 | MN30-F03 | 2 | 20 | 1 | 86 |  |  | RestartCompleted (Work Order) | M201 |  | M04 | 30000H Repl Articulation 16M
6042.10.02.61-GR001-STRC | Structure G5008 | PHRN01 | 30319146 | 21423845 | 30000H Ovhl Ripper Frame G5008 | Ovhl Articulation G5008 |  | 2027/11 | 2027-03-20 | MN30-F01 | 1 | 20 | 2 | 86 |  |  | Cycle StartHold (Work Order) | M201 |  | M04 | 30000H Ovhl Ripper Frame 16M
6042.10.02.61-GR001-STRC | Structure G5008 | PHRN01 | 30316759 | 20450434 | 30000H Repl Cab Mount G5008 | Repl Cab Mount G5008 |  | 2030/05 | 2030-01-31 | MN30-F01 | 2 | 10 | 1 | 86 |  |  | Cycle StartHold (Work Order) | M201 |  | M04 | 30000H Repl Cab Mount 16M
6042.10.02.61-GR002-STRC | Structure G5009 | PHRN01 | 30732091 | 21140101 | 30000H Repl Cab Mount G5009 | Repl Cab Mount G5009 | 4200922311 | 2020/35 | 2020-08-28 | MN30-F01 | 2 | 10 | 1 | 86 |  |  | RestartCompleted (Work Order) | M201 |  | M04 | 30000H Repl Cab Mount 16M
6042.10.02.61-GR004-STRC | Structure G5010 | PHRN01 | 30770348 | 21201146 | 30000H Repl Cab Mount G5010 | Repl Cab Mount G5010 | 4200545353 | 2020/12 | 2020-03-19 | MN30-F03 | 2 | 10 | 1 | 86 |  |  | RestartCompleted (Work Order) | M201 |  | M04 | 30000H Repl Cab Mount 16M
6042.10.02.61-GR005-STRC | Structure G5011 | PHRN01 | 30770394 | 21201197 | 30000H Ovhl Ripper Frame G5011 | Ovhl Articulation G5011 |  | 2024/17 | 2024-04-25 | MN30-F01 | 1 | 20 | 2 | 86 |  |  | Cycle StartHold (Work Order) | M201 |  | M04 | 30000H Ovhl Ripper Frame 16M
6042.10.02.61-GR005-STRC | Structure G5011 | PHRN01 | 30770397 | 21201201 | 30000H Repl Cab Mount G5011 | Repl Cab Mount G5011 | 4200512684 | 2020/13 | 2020-03-29 | MN30-F03 | 2 | 10 | 1 | 86 |  |  | RestartCompleted (Work Order) | M201 |  | M04 | 30000H Repl Cab Mount 16M
6042.10.02.61-GR006-STRC | Structure G5012 | PHRN01 | 30877413 | 21402731 | 30000H Ovhl Articulation G5012 | Ovhl Articulation G5012 |  | 2025/07 | 2025-02-12 | MN30-F01 | 2 | 20 | 1 | 86 |  |  | Cycle StartHold (Work Order) | M201 |  | M04 | 30000H Ovhl Articulation 18M3
6042.10.02.61-GR006-STRC | Structure G5012 | PHRN01 | 30877413 | 21402730 | 30000H Ovhl Ripper Frame G5012 | Ovhl Articulation G5012 |  | 2025/07 | 2025-02-12 | MN30-F01 | 1 | 20 | 1 | 86 |  |  | Cycle StartHold (Work Order) | M201 |  | M04 | 30000H Ovhl Ripper Frame 18M3
6042.10.02.61-GR006-STRC | Structure G5012 | PHRN01 | 30877413 | 21402729 | 30000H Ovhl Steering Link G5012 | Ovhl Articulation G5012 |  | 2025/07 | 2025-02-12 | MN30-F01 | 1 | 20 | 1 | 86 |  |  | Cycle StartHold (Work Order) | M201 |  | M04 | 30000H Ovhl Steering Link 18M3
6042.10.02.61-GR006-STRC | Structure G5012 | PHRN01 | 30877410 | 21402727 | 30000H Repl Cab Mount G5012 | Repl Cab Mount G5012 |  | 2025/07 | 2025-02-12 | MN30-F01 | 2 | 10 | 1 | 86 |  |  | Cycle StartHold (Work Order) | M201 |  | M04 | 30000H Repl Cab Mount 18M3
6042.10.02.61-GR001 | Grader Caterpillar 16M G5008 | TWKN01 | 30319873 | 21387906 | 60M Stat Audit Fire System QTEC G5008 | Stat Audit Fire Systems G5008 | 4200796737 | 2019/45 | 2019-11-07 | MN30-F01 | 1 | 10.5 | 14 | 93 |  |  | Cycle StartCompleted (Work Order) | M201 |  | M03 | 60M Stat Audit Fire System HYBRID 16M
6042.10.02.61-GR004 | Grader Caterpillar 16M G5010 | TWKN01 | 30769627 | 21387908 | 60M Stat Audit Fire System QTEC G5010 | Stat Audit Fire Systems G5010 | 4200794721 | 2020/21 | 2020-05-24 | MN30-F01 | 1 | 10.5 | 10 | 93 |  |  | ScheduledCompleted (Work Order) | M201 |  | M03 | 60M Stat Audit Fire System QTEC 16M
6042.10.02.61-GR005 | Grader Caterpillar 16M G5011 | TWKN01 | 30769628 | 21387910 | 60M Stat Audit Fire System QTEC G5011 | Stat Audit Fire Systems G5011 | 4201022572 | 2020/21 | 2020-05-18 | MN30-F01 | 1 | 10.5 | 10 | 93 |  |  | ScheduledCompleted (Work Order) | M201 |  | M03 | 60M Stat Audit Fire System QTEC 16M
6042.10.02.61-GR006 | Grader Caterpillar 18M3 G5012 | TWKN01 | 30870595 | 21389743 | 60M Stat Audit Fire System QTEC G5012 | Stat Audit Fire Systems G5012 |  | 2024/25 | 2024-06-18 | MN30-F07 | 1 | 10 | 10 | 93 |  |  | ScheduledHold (Work Order) | M201 |  | M03 | 60M Stat Audit Fire Systems 18M3